## Start Here
AI Pilot Scorecard
From outshined.io - How to Run Your First AI Pilot Project
1. Fill in the Charter tab before the pilot starts.
2. For 1-2 weeks BEFORE the pilot, log each task on the Baseline Log tab.
3. During the pilot (weeks 2-4), log each task on the Pilot Log tab the same way.
4. The Scorecard tab calculates the comparison and estimated ROI automatically.
Only edit the yellow cells on the Scorecard.
Quality score: reviewer rates a sample of outputs 1-5 on accuracy, tone and completeness.
Rework: enter Y if the output had to be sent back for fixes, otherwise N.
Incident: enter Y if AI output was wrong in a way that mattered, or sensitive data was entered by mistake.

## Charter
Pilot Charter
One page. Agree on this before anyone opens a tool.
Item | Your answer
Pilot question
Workflow being tested
Pilot owner
Pilot users (3-8 people)
Tool and plan
Start date
End date
Success: expand if...
Adjust if...
Stop if...
Data that must NOT go into the tool
Who reviews AI output
Decision (expand / adjust / stop)
Lessons learned

## Baseline Log
Baseline Log
Log every task for 1-2 weeks BEFORE the pilot.
Date | User | Task description | Minutes | Quality (1-5) | Rework (Y/N) | Incident (Y/N)

## Pilot Log
Pilot Log
Log every task during the pilot, the same way as the baseline.
Date | User | Task description | Minutes | Quality (1-5) | Rework (Y/N) | Incident (Y/N)

## Scorecard
Scorecard
Calculated from the two logs. Edit only the yellow cells.
Measure | Baseline | Pilot | Change
Tasks logged | 0 | 0
Average minutes per task | 0 | 0 | 0%
Average quality score (1-5) | 0 | 0 | 0
Rework rate | 0% | 0% | 0%
Incidents | n/a | 0
ROI estimate | Value
Tasks per week (whole team, after rollout) | 20
Loaded hourly cost of the people doing it ($) | 60
Number of licensed users | 5
License cost per user per month ($) | 30
Minutes saved per task | 0
Hours saved per month | 0
Value of time saved per month ($) | 0
License cost per month ($) | 150
Net value per month ($) | -150
Net value per year ($) | -1800
Count saved time as value only if it goes to billable or higher-value work. Be conservative.